![C:\Users\wow\AppData\Local\Microsoft\Windows\Temporary Internet Files\Content.IE5\G2J91E90\MC900438219[1].wmf]()

**Goal:** To have a litter free playground.

**Steps:**

Find out how much litter is in our playground.

Get everyone to think about ways to reduce/eliminate litter.

Think of ways to involve everyone in making our playground a litter free zone.

|  |  |  |
| --- | --- | --- |
| Action | Who’s responsible? | Time target |
| Find out how much litter is in our playground. | Eco Committee  | October 2011 |
| Find out how many bins are in the playground and if they are in the correct places.  | Eco CommitteeJanitor | October 2011 |
| Label and distribute litter pickers and rotas into each class.  | Eco CommitteeAll pupils and staff | December 2011 |
| Monitor how successful the litter picking rota is and make changes if needed. | Eco Committee | Ongoing |
| Have regular assemblies to raise the awareness of litter. | Eco committeeWhole school | Ongoing |
| Put information on the school website, Eco Noticeboard and in local library and church. | Eco CommitteeMrs Hunter/Miss Malcolm | Ongoing |
| Register for and take part in Keep Scotland Beautiful's National Spring Clean. | Eco Committee Parent helpers | May 2012May 2013 |
| Organise a litter relay in the playground. | Eco CommitteeParent HelpersAll pupils | May 2012 |
| Think about writing and school litter policy. | Eco CommitteeAll pupils and staff | June 2013 |